## PWP & Amendments
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
ANNUAL FUNDING SOURCES TABLE
Foothills RPO
TASK CODE | WORK CATEGORY | RPO PROGRAM FUNDS |  |  |  | Q1 Amendment |  |  | Q2 Amendment |  |  | Q3 Amendment |  |  | Q4 Amendment
|  | LOCAL 20% | State 0% | FEDERAL 80% | TOTAL | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX
[6 empty] | Original Budgeted Amount | Net Change | New 1st Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 2nd Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 3rd Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 4th Quarter Budgeted Amount
I. DATA COLLECTION AND ASSESSMENT | [5 empty] | I. DATA COLLECTION AND ASSESSMENT |  |  | I. DATA COLLECTION AND ASSESSMENT |  |  | I. DATA COLLECTION AND ASSESSMENT |  |  | I. DATA COLLECTION AND ASSESSMENT
I-1 | DATA COLLECTION AND ASSESSMENT | 2000 | 0 | 8000 | 10000 | 10000 |  | 10000 | 10000 |  | 10000 | 10000 |  | 10000 | 10000 |  | 10000
I-1.1 | Highway |  |  |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another.
I-1.2 | Other Modes
I-1.3 | Socioeconomic
I-1.4 | Title VI
II. TRANSPORTATION PLANNING | [5 empty] | II. TRANSPORTATION PLANNING |  |  | II. TRANSPORTATION PLANNING |  |  | II. TRANSPORTATION PLANNING |  |  | II. TRANSPORTATION PLANNING
II-1 | COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT | 1300 | 0 | 5200 | 6500 | 6500 |  | 6500 | 6500 |  | 6500 | 6500 |  | 6500 | 6500 |  | 6500
II-1.1 | Develop CTP Vision |  |  |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another.
II-1.2 | Conduct CTP Needs Assessment
II-1.3 | Analyze Alternatives and Environmental Screening
II-1.4 | Develop Final Plan
II-1.5 | Adopt Plan
II-2 | PRIORITIZATION | 1000 | 0 | 4000 | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000
II-2.1 | Project Prioritization |  |  |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another.
II-3 | PROGRAM AND PROJECT DEVELOPMENT | 2850 | 0 | 11400 | 14250 | 14250 |  | 14250 | 14250 |  | 14250 | 14250 |  | 14250 | 14250 |  | 14250
II-3.1 | STIP Participation |  |  |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another.
II-3.2 | Merger / Project Development
II-4 | GENERAL TRANSPORTATION PLANNING | 4900 | 0 | 19600 | 24500 | 24500 |  | 24500 | 24500 |  | 24500 | 24500 |  | 24500 | 24500 |  | 24500
II-4.1 | Regional and Statewide Planning |  |  |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another.
II-4.2 | Special Studies, Projects and Other Trainings
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES | [5 empty] | III. ADMINISTRATION OF TRANS PLANNING & POLICES |  |  | III. ADMINISTRATION OF TRANS PLANNING & POLICES |  |  | III. ADMINISTRATION OF TRANS PLANNING & POLICES |  |  | III. ADMINISTRATION OF TRANS PLANNING & POLICES
III-1 | ADMINISTRATIVE ACTIVITIES | 3700 | 0 | 14800 | 18500 | 18500 |  | 18500 | 18500 |  | 18500 | 18500 |  | 18500 | 18500 |  | 18500
III-1.1 | Administrative Documents |  |  |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another. |  |  | Provide explanation for moving funds from one category to another.
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance
III-1.3 | Program Administration
IV. DIRECT COSTS | [5 empty] | IV. DIRECT COSTS |  |  | IV. DIRECT COSTS |  |  | IV. DIRECT COSTS |  |  | IV. DIRECT COSTS
IV-1 | PROGRAMMATIC DIRECT CHARGES | 2305 | 0 | 9220 | 11525 | 11525 |  | 11525 | 11525 |  | 11525 | 11525 |  | 11525 | 11525 |  | 11525
IV-1.1 | Program-wide Direct Costs |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
IV-2 | ADVERTISING | 100 | 0 | 400 | 500 | 500 |  | 500 | 500 |  | 500 | 500 |  | 500 | 500 |  | 500
IV-2.1 | News Media Ads |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
IV-3 | LODGING, MEALS, INCIDENTALS | 360 | 0 | 1440 | 1800 | 1800 |  | 1800 | 1800 |  | 1800 | 1800 |  | 1800 | 1800 |  | 1800
IV-3.1 | Hotel Costs |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
IV-3.2 | Meal Costs
IV-3.3 | Incidentals
IV-4 | POSTAGE | 100 | 0 | 400 | 500 | 500 |  | 500 | 500 |  | 500 | 500 |  | 500 | 500 |  | 500
IV-4.1 | Mailings |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
IV-5 | REGISTRATION / TRAINING | 484 | 0 | 1936 | 2420 | 2420 |  | 2420 | 2420 |  | 2420 | 2420 |  | 2420 | 2420 |  | 2420
IV-5.1 | Conference Registration |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
IV-5.2 | Meeting / Workshop / Training Fees
IV-6 | TRAVEL | 1100 | 0 | 4400 | 5500 | 5500 |  | 5500 | 5500 |  | 5500 | 5500 |  | 5500 | 5500 |  | 5500
IV-6.1 | Mileage Reimbursement |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
IV-6.2 | Car Rental Costs
IV-6.3 | Other Travel Expenses
V. INDIRECT COSTS | [5 empty] | V. INDIRECT COSTS |  |  | V. INDIRECT COSTS |  |  | V. INDIRECT COSTS |  |  | V. INDIRECT COSTS
V-1 | INDIRECT COSTS | 6394.8 | 0 | 25579.2 | 31974 | 31974 |  | 31974 | 31974 |  | 31974 | 31974 |  | 31974 | 31974 |  | 31974
V-1.1 | Incurred Indirect Costs |  |  |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another |  |  | Provide explanation for moving funds from one category to another
RPO OPERATIONAL EXPENSE TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | 132969 | 0 | 132969 | 132969 | 0 | 132969 | 132969 | 0 | 132969 | 132969 | 0 | 132969
Approved by the TAC on: ____________20__
Signature, TAC Chairman
Signature, RPO Secretary

## Special Study 1
Special Study for Planning Work Program
WBS # | 50343.4.20
PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
TASK CODE | WORK CATEGORY | SPR PROGRAM FUNDS |  |  |  | Q1 Amendment |  |  | Q2 Amendment |  |  | Q3 Amendment |  |  | Q4 Amendment
|  | LOCAL | STATE | FEDERAL | TOTAL | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX
[6 empty] | Original Budgeted Amount | Net Change | New 1st Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 2nd Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 3rd Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 4th Quarter Budgeted Amount
|  | 5% | 15% | 80% | 100%
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS | [5 empty] | VI. SPECIAL STUDY SPR FUNDS |  |  | VI. SPECIAL STUDY SPR FUNDS |  |  | VI. SPECIAL STUDY SPR FUNDS |  |  | VI. SPECIAL STUDY SPR FUNDS
VI-1 | SPECIAL SPR ALLOCATION | 4750 | 14250 | 76000 | 95000 | 95000 |  | 95000 | 95000 |  | 95000 | 95000 | 0 | 95000 | 95000 | 0 | 95000
VI-1.1 | Fonta Flora Trail Feasibility Study |  |  |  |  | Can not modify Special Study amount |  |  | Can not modify Special Study amount |  |  | Can not modify Special Study amount |  |  | Can not modify Special Study amount
SPECIAL SPR PROJECT TOTAL |  | 4750 | 14250 | 76000 | 95000 | 95000 | 0 | 95000 | 95000 | 0 | 95000 | 95000 | 0 | 95000 | 95000 | 0 | 95000
PWP TOTAL with one special study |  | 31343.8 | 14250 | 182375.2 | 227969 | 227969 | 0 | 227969 | 227969 | 0 | 227969 | 227969 | 0 | 227969 | 227969 | 0 | 227969
Special Study Narrative
This study will be performed by an outside consultant. McDowell County currently has project EB-5916 in progress that will construct a trail from Resistoflex Road in Marion and end along Robey Conley Road, approximately 0.2 miles from Highway 70. However,a study needs to be performed that would examine all possible routes for a trail from where EB-5916 stops on Robey Conley Road in Marion, across Highway 70, to an existing trail along the Catawba River, Joseph McDowell Greenway.
Approved by the TAC on: ____________20__
__________________________________________________
Signature, TAC Chairman
__________________________________________________
Signature, RPO Secretary
|  | WBS # | 50343.4.20
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Fonta Flora Trail Feasibility Study
1st Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 1st QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 95000
0
| Total: | 0 | 0% | 0 | 95000
| Federal Share: | 0 |  | 0 | 76000
| State Share: | 0 |  | 0 | 14250
| Local Share: | 0 |  | 0 | 4750
| RPO Special Study Q1 reimbursement | 0
Insert narrative of work accomplished for Q1. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.
|  | WBS # | 50343.4.20
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Fonta Flora Trail Feasibility Study
2nd Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 2nd QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 95000
0
| Total: | 0 | 0% | 0 | 95000
| Federal Share: | 0 |  | 0 | 76000
| State Share: | 0 |  | 0 | 14250
| Local Share: | 0 |  | 0 | 4750
| RPO Special Study Q2 reimbursement | 0
Insert narrative of work accomplished for Q2. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.
|  | WBS # | 50343.4.20
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Fonta Flora Trail Feasibility Study
3rd Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 3rd QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 95000
0
| Total: | 0 | 0% | 0 | 95000
| Federal Share: | 0 |  | 0 | 76000
| State Share: | 0 |  | 0 | 14250
| Local Share: | 0 |  | 0 | 4750
| RPO Special Study Q2 reimbursement | 0
Insert narrative of work accomplished for Q3. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.
|  | WBS # | 50343.4.20
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Fonta Flora Trail Feasibility Study
4th Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 4th QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 95000
0
| Total: | 0 | 0% | 0 | 95000
| Federal Share: | 0 |  | 0 | 76000
| State Share: | 0 |  | 0 | 14250
| Local Share: | 0 |  | 0 | 4750
| RPO Special Study Q2 reimbursement | 0
Insert narrative of work accomplished for Q4. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.

## Special Study 2
Special Study #2 for Planning Work Program
WBS # | 50343.4.21
PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
TASK CODE | WORK CATEGORY | SPR PROGRAM FUNDS |  |  |  | Q1 Amendment |  |  | Q2 Amendment |  |  | Q3 Amendment |  |  | Q4 Amendment
|  | LOCAL | STATE | FEDERAL | TOTAL | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX |  |  | Date: Day/Month/20XX
[6 empty] | Original Budgeted Amount | Net Change | New 1st Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 2nd Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 3rd Quarter Budgeted Amount | Original Budget With Previous Q Amendment(s) | Net Change | New 4th Quarter Budgeted Amount
|  | 5% | 15% | 80% | 100%
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS | [5 empty] | VI. SPECIAL STUDY SPR FUNDS |  |  | VI. SPECIAL STUDY SPR FUNDS |  |  | VI. SPECIAL STUDY SPR FUNDS |  |  | VI. SPECIAL STUDY SPR FUNDS
VI-1 | SPECIAL SPR ALLOCATION | 4000 | 12000 | 64000 | 80000 | 80000 |  | 80000 | 80000 |  | 80000 | 80000 | 0 | 80000 | 80000 | 0 | 80000
VI-1.1 | Henderson-Logan Complete Steeets Charrette |  |  |  |  | Can not modify Special Study amount |  |  | Can not modify Special Study amount |  |  | Can not modify Special Study amount |  |  | Can not modify Special Study amount
SPECIAL SPR PROJECT TOTAL |  | 4000 | 12000 | 64000 | 80000 | 80000 | 0 | 80000 | 80000 | 0 | 80000 | 80000 | 0 | 80000 | 80000 | 0 | 80000
PWP TOTAL with 2 special studies |  | 35343.8 | 26250 | 246375.2 | 307969 | 307969 | 0 | 307969 | 307969 | 0 | 307969 | 307969 | 0 | 307969 | 307969 | 0 | 307969
Special Study Narrative
This charrette will be performed by an outside consultant. This will study how to convert the existing Logan Street and Henderson Street Corridor to a complete streets corridor that improves safety and is multi-modal.
Approved by the TAC on: ____________20__
__________________________________________________
Signature, TAC Chairman
__________________________________________________
Signature, RPO Secretary
|  | WBS # | 50343.4.21
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Henderson-Logan Complete Steeets Charrette
1st Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 1st QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 80000
0
| Total: | 0 | 0% | 0 | 80000
| Federal Share: | 0 |  | 0 | 64000
| State Share: | 0 |  | 0 | 12000
| Local Share: | 0 |  | 0 | 4000
| RPO Special Study Q1 reimbursement | 0
Insert narrative of work accomplished for Q1. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.
|  | WBS # | 50343.4.21
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Henderson-Logan Complete Steeets Charrette
2nd Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 2nd QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 80000
0
| Total: | 0 | 0% | 0 | 80000
| Federal Share: | 0 |  | 0 | 64000
| State Share: | 0 |  | 0 | 12000
| Local Share: | 0 |  | 0 | 4000
| RPO Special Study Q2 reimbursement | 0
Insert narrative of work accomplished for Q2. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.
|  | WBS # | 50343.4.21
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Henderson-Logan Complete Steeets Charrette
3rd Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 3rd QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 80000
0
| Total: | 0 | 0% | 0 | 80000
| Federal Share: | 0 |  | 0 | 64000
| State Share: | 0 |  | 0 | 12000
| Local Share: | 0 |  | 0 | 4000
| RPO Special Study Q2 reimbursement | 0
Insert narrative of work accomplished for Q3. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.
|  | WBS # | 50343.4.21
|  | PO # | 7500025356
FY 2023 (July 1, 2022-June 30, 2023)
Foothills RPO
Henderson-Logan Complete Steeets Charrette
4th Quarter expenses incurred July 1 - September 30
SPR Expenditures
|  | 4th QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
VI. SPECIAL STATE PLANNING & RESEARCH FUNDS
|  | 0 | 0% | 0 | 80000
0
| Total: | 0 | 0% | 0 | 80000
| Federal Share: | 0 |  | 0 | 64000
| State Share: | 0 |  | 0 | 12000
| Local Share: | 0 |  | 0 | 4000
| RPO Special Study Q2 reimbursement | 0
Insert narrative of work accomplished for Q4. Be sure to include consultant invoices and description of work for each of their invoices, along with proof of payment.

## PWP Narrative
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
Narrative
Foothills RPO
I. DATA COLLECTION AND ASSESSMENT
I-1 DATA COLLECTION AND ASSESSMENT |  | 10000
I-1.1 | Highway
Perform traffic counts and crash analyses for all three counties
I-1.2 | Other Modes
Attend County transit system TAB meetings (~12-15 meetings). Gather data for submission of projects in SPOT. Continue bike/ped counting on TBRT and Purple Martin Greenway
I-1.3 | Socioeconomic
I-1.4 | Title VI
Update Maps
II. TRANSPORTATION PLANNING
II-1 COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT |  | 6500
II-1.1 | Develop CTP Vision
II-1.2 | Conduct CTP Needs Assessment
II-1.3 | Analyze Alternatives and Environmental Screening
II-1.4 | Develop Final Plan
Review Draft
II-1.5 | Adopt Plan
Finish adopting Regional CTP
II-2 PRIORITIZATION |  | 5000
II-2.1 | Project Prioritization
Start work on SPOT 7.0
II-3 PROGRAM AND PROJECT DEVELOPMENT |  | 14250
II-3.1 | STIP Participation
Finish work on 2024-2033 STIP, including meetings, and public involvement. Continue to respond to requests for information and project meetings
II-3.2 | Merger / Project Development
II-4 GENERAL TRANSPORTATION PLANNING |  | 24500
II-4.1 | Regional and Statewide Planning
Continue on IPD, Committee work for NCARPO including Great Trails Plan, STC, SPOT Workgroup, PEL, Bike and Ped and others as requested.
II-4.2 | Special Studies, Projects and Other Trainings
Coduct any SPR studies that are funded, finalize SPR currently underway, serve on steering committee for IMD project in McDowell County. Continue work on the IRPO website including online mapping, and Continue work on the IRPO website including online mapping, . Continue to improve on ArcGIS Pro, and data visualizations. NCAMPO, NC APA, Bike Summit, Active Routes to School, Carolina Thread Trail Summit, NC GIS, NCAUG, WTS Meetings, MRGAC (GIS quarterly meeting in Asheville), ESRI Seminars, NCAUG and National RPO meeting, as time allows.
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 ADMINISTRATIVE ACTIVITIES |  | 18500
III-1.1 | Administrative Documents
Prepare, obtain approval, and submit PWP, and needed amendments. Prepare and submit Quarterly Reports and Final Yearly Narrative. Updatae MOU or PIP as needed.
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance
Prepare minutes, agendas, materials, speakers, etc. for and hold 6 TCC and 6 TAC meetings. Inform TAC of Ethics information and deadlines. Assist TAC members with Ethics forms. Work with other western RPOs to continue to improve as RPOs. Mentor new Directors
III-1.3 | Program Administration
Providing transportation information and data. Contact NCDOT staff concerning questions from officials, citizens and TAC /TCC members. Phone calls, emails, etc.
IV. DIRECT COSTS
IV-1 PROGRAMMATIC DIRECT CHARGES |  | 11525
IV-1.1 | Program-wide Direct Costs
Regular costs for operation of the RPO program including website, computer support, supplies, equipment purchases (planning to purchase bike/ped counters), part of GIS software costs (maintenance), and dues.
IV-2 ADVERTISING |  | 500
IV-2.1 | News Media Ads
Advertising costs for workshops, public hearings and public comment periods.
IV-3 LODGING, MEALS, INCIDENTALS |  | 1800
IV-3.1 | Hotel Costs
Costs for overnight stays at approved trainings and conferences
IV-3.2 | Meal Costs
Meal Costs while on overnight or extended travel
IV-3.3 | Incidentals
Hotel parking, tips
IV-4 POSTAGE |  | 500
IV-4.1 | Mailings
Costs for mailing RPO projects (surveys, notices, etc.)
IV-5 REGISTRATION / TRAINING |  | 2420
IV-5.1 | Conference Registration
NCAMPO, NC APA, Bike Summit, Active Routes to School, Carolina Thread Trail Summit, NC GIS, NCAUG, ESRI Seminars, National RPO and other conferences, and workshops that approved
IV-5.2 | Meeting / Workshop / Training Fees
WTS Meetings, MRGAC (GIS quarterly meeting in Asheville), other trainings as approved
IV-6 TRAVEL |  | 5500
IV-6.1 | Mileage Reimbursement
Reimbursement for total miles traveled
IV-6.2 | Car Rental Costs
IV-6.3 | Other Travel Expenses
Parking fee, air fare, other
V. INDIRECT COSTS
V-1 INDIRECT COSTS APPROVED BY COGNIZANT AGENCY |  | 31974
V-1.1 | Incurred Indirect Costs
HHS Approved Rate of 54% (only applies to salaries. Fringe rate is estimated at 33%)
RPO OPERATIONAL EXPENSE TOTAL |  | 132969

## Q1 Expenditures
FY 2023 (July 1, 2022-June 30, 2023) | [5 empty] | FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM | [5 empty] | FIRST QUARTER - QUARTERLY EXPENDITURE SUMMARY
ANNUAL FUNDING SOURCES TABLE | [5 empty] | Foothills RPO
Foothills RPO
TASK CODE | WORK CATEGORY | RPO PROGRAM FUNDS |  |  |  |  | RPO Expenditures-1st Quarter expenses incurred July 1 - September 30
|  | LOCAL 20% | STATE 0% | FEDERAL 80% | TOTAL |  | 1st QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
I. DATA COLLECTION AND ASSESSMENT | [6 empty] | I. DATA COLLECTION AND ASSESSMENT
I-1 | DATA COLLECTION AND ASSESSMENT | 2000 | 0 | 8000 | 10000 |  | 0 | 0% | 0 | 10000
I-1.1 | Highway | [7 empty] | 0
I-1.2 | Other Modes | [7 empty] | 0
I-1.3 | Socioeconomic | [7 empty] | 0
I-1.4 | Title VI | [7 empty] | 0
II. TRANSPORTATION PLANNING | [6 empty] | II. TRANSPORTATION PLANNING
II-1 | CTP DEVELOPMENT | 1300 | 0 | 5200 | 6500 |  | 0 | 0% | 0 | 6500
II-1.1 | Develop CTP Vision | [7 empty] | 0
II-1.2 | Conduct CTP Needs Assessment | [7 empty] | 0
II-1.3 | Analyze Alternatives and Environmental Screening | [7 empty] | 0
II-1.4 | Develop Final Plan | [7 empty] | 0
II-1.5 | Adopt Plan | [7 empty] | 0
II-2 | PRIORITIZATION | 1000 | 0 | 4000 | 5000 |  | 0 | 0% | 0 | 5000
II-2.1 | Project Prioritization | [7 empty] | 0
II-3 | PROGRAM AND PROJECT DEVELOPMENT | 2850 | 0 | 11400 | 14250 |  | 0 | 0% | 0 | 14250
II-3.1 | STIP Participation | [7 empty] | 0
II-3.2 | Merger / Project Development | [7 empty] | 0
II-4 | GENERAL TRANSPORTATION PLANNING | 4900 | 0 | 19600 | 24500 |  | 0 | 0% | 0 | 24500
II-4.1 | Regional and Statewide Planning | [7 empty] | 0
II-4.2 | Special Studies, Projects and Other Trainings | [7 empty] | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES | [6 empty] | III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 | ADMINISTRATIVE ACTIVITIES | 3700 | 0 | 14800 | 18500 |  | 0 | 0% | 0 | 18500
III-1.1 | Administrative Documents | [7 empty] | 0
III-1.2 | TCC/TAC Work Facilitation; Ethics Compliance | [7 empty] | 0
III-1.3 | Program Administration | [7 empty] | 0
IV. DIRECT COSTS | [6 empty] | IV. DIRECT COSTS
IV-1 | PROGRAMMATIC DIRECT CHARGES | 2305 | 0 | 9220 | 11525 |  | 0 | 0% | 0 | 11525
IV-1.1 | Program-wide Direct Costs | [7 empty] | 0
IV-2 | ADVERTISING | 100 | 0 | 400 | 500 |  | 0 | 0% | 0 | 500
IV-2.1 | News Media Ads | [7 empty] | 0
IV-3 | LODGING, MEALS, INCIDENTALS | 360 | 0 | 1440 | 1800 |  | 0 | 0% | 0 | 1800
IV-3.1 | Hotel Costs | [7 empty] | 0
IV-3.2 | Meal Costs | [7 empty] | 0
IV-3.3 | Incidentals | [7 empty] | 0
IV-4 | POSTAGE | 100 | 0 | 400 | 500 |  | 0 | 0% | 0 | 500
IV-4.1 | Mailings | [7 empty] | 0
IV-5 | REGISTRATION / TRAINING | 484 | 0 | 1936 | 2420 |  | 0 | 0% | 0 | 2420
IV-5.1 | Conference Registration | [7 empty] | 0
IV-5.2 | Meeting / Workshop / Training Fees | [7 empty] | 0
IV-6 | TRAVEL | 1100 | 0 | 4400 | 5500 |  | 0 | 0% | 0 | 5500
IV-6.1 | Mileage Reimbursement | [7 empty] | 0
IV-6.2 | Car Rental Costs | [7 empty] | 0
IV-6.3 | Other Travel Expenses | [7 empty] | 0
V. INDIRECT COSTS | [6 empty] | V. INDIRECT COSTS
IV-1 | INDIRECT COSTS | 6394.8 | 0 | 25579.2 | 31974 |  | 0 | 0% | 0 | 31974
IV-1.1 | Incurred Indirect Costs | [7 empty] | 0
TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total: | 0 | 0% | 0 | 132969
[6 empty] | Federal Share: | 0 |  | 0 | 106375.2
[6 empty] | Local Share: | 0 |  | 0 | 26593.8
[6 empty] | RPO Operations Q1 reimbursement | 0
RPO Operational Expense TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total Expense | 0 | 0% | 0 | 132969

## Q1 Narrative
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
1st Quarter Narrative
Foothills RPO
I. DATA COLLECTION AND ASSESSMENT
I-1 DATA COLLECTION AND ASSESSMENT |  | 0
I-1.1 | Highway | 0
I-1.2 | Other Modes | 0
I-1.3 | Socioeconomic | 0
I-1.4 | Title VI | 0
II. TRANSPORTATION PLANNING
II-1 COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT |  | 0
II-1.1 | Develop CTP Vision | 0
II-1.2 | Conduct CTP Needs Assessment | 0
II-1.3 | Analyze Alternatives and Environmental Screening | 0
II-1.4 | Develop Final Plan | 0
II-1.5 | Adopt Plan | 0
II-2 PRIORITIZATION |  | 0
II-2.1 | Project Prioritization | 0
II-3 PROGRAM AND PROJECT DEVELOPMENT |  | 0
II-3.1 | STIP Participation | 0
II-3.2 | Merger / Project Development | 0
II-4 GENERAL TRANSPORTATION PLANNING |  | 0
II-4.1 | Regional and Statewide Planning | 0
II-4.2 | Special Studies, Projects and Other Trainings | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 ADMINISTRATIVE ACTIVITIES |  | 0
III-1.1 | Administrative Documents | 0
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance | 0
III-1.3 | Program Administration | 0
IV. DIRECT COSTS
IV-1 PROGRAMMATIC DIRECT CHARGES |  | 0
IV-1.1 | Program-wide Direct Costs | 0
IV-2 ADVERTISING |  | 0
IV-2.1 | News Media Ads | 0
IV-3 LODGING, MEALS, INCIDENTALS |  | 0
IV-3.1 | Hotel Costs | 0
IV-3.2 | Meal Costs | 0
IV-3.3 | Incidentals | 0
IV-4 POSTAGE |  | 0
IV-4.1 | Mailings | 0
IV-5 REGISTRATION / TRAINING |  | 0
IV-5.1 | Conference Registration | 0
IV-5.2 | Meeting / Workshop / Training Fees | 0
IV-6 TRAVEL |  | 0
IV-6.1 | Mileage Reimbursement | 0
IV-6.2 | Car Rental Costs | 0
IV-6.3 | Other Travel Expenses | 0
V. INDIRECT COSTS
V-1 INDIRECT COSTS |  | 0
V-1.1 | Incurred Indirect Costs | 0
RPO Operational Expense TOTAL |  | 0

## Q2 Expenditures
FY 2023 (July 1, 2022-June 30, 2023) | [5 empty] | FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM | [5 empty] | 2nd QUARTER - QUARTERLY EXPENDITURE SUMMARY
ANNUAL FUNDING SOURCES TABLE | [5 empty] | Foothills RPO
Foothills RPO
TASK CODE | WORK CATEGORY | RPO PROGRAM FUNDS |  |  |  |  | RPO Expenditures - 2nd Quarter expenses incurred October 1 - December 31
|  | LOCAL 20% | STATE 0% | FEDERAL 80% | TOTAL |  | 1st QUARTER EXPENDITURES | 2nd QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
I. DATA COLLECTION AND ASSESSMENT | [6 empty] | I. DATA COLLECTION AND ASSESSMENT
I-1 | DATA COLLECTION AND ASSESSMENT | 2000 | 0 | 8000 | 10000 |  | 0 | 0 | 0% | 0 | 10000
I-1.1 | Highway | [5 empty] | 0 |  |  | 0
I-1.2 | Other Modes | [5 empty] | 0 |  |  | 0
I-1.3 | Socioeconomic | [5 empty] | 0 |  |  | 0
I-1.4 | Title VI | [5 empty] | 0 |  |  | 0
II. TRANSPORTATION PLANNING | [6 empty] | II. TRANSPORTATION PLANNING
II-1 | CTP DEVELOPMENT | 1300 | 0 | 5200 | 6500 |  | 0 | 0 | 0% | 0 | 6500
II-1.1 | Develop CTP Vision | [5 empty] | 0 |  |  | 0
II-1.2 | Conduct CTP Needs Assessment | [5 empty] | 0 |  |  | 0
II-1.3 | Analyze Alternatives and Environmental Screening | [5 empty] | 0 |  |  | 0
II-1.4 | Develop Final Plan | [5 empty] | 0 |  |  | 0
II-1.5 | Adopt Plan | [5 empty] | 0 |  |  | 0
II-2 | PRIORITIZATION | 1000 | 0 | 4000 | 5000 |  | 0 | 0 | 0% | 0 | 5000
II-2.1 | Project Prioritization | [5 empty] | 0 |  |  | 0
II-3 | PROGRAM AND PROJECT DEVELOPMENT | 2850 | 0 | 11400 | 14250 |  | 0 | 0 | 0% | 0 | 14250
II-3.1 | STIP Participation | [5 empty] | 0 |  |  | 0
II-3.2 | Merger / Project Development | [5 empty] | 0 |  |  | 0
II-4 | GENERAL TRANSPORTATION PLANNING | 4900 | 0 | 19600 | 24500 |  | 0 | 0 | 0% | 0 | 24500
II-4.1 | Regional and Statewide Planning | [5 empty] | 0 |  |  | 0
II-4.2 | Special Studies, Projects and Other Trainings | [5 empty] | 0 |  |  | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES | [6 empty] | III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 | ADMINISTRATIVE ACTIVITIES | 3700 | 0 | 14800 | 18500 |  | 0 | 0 | 0% | 0 | 18500
III-1.1 | Administrative Documents | [5 empty] | 0 |  |  | 0
III-1.2 | TCC/TAC Work Facilitation; Ethics Compliance | [5 empty] | 0 |  |  | 0
III-1.3 | Program Administration | [5 empty] | 0 |  |  | 0
IV. DIRECT COSTS | [6 empty] | IV. DIRECT COSTS
IV-1 | PROGRAMMATIC DIRECT CHARGES | 2305 | 0 | 9220 | 11525 |  | 0 | 0 | 0% | 0 | 11525
IV-1.1 | Program-wide Direct Costs | [5 empty] | 0 |  |  | 0
IV-2 | ADVERTISING | 100 | 0 | 400 | 500 |  | 0 | 0 | 0% | 0 | 500
IV-2.1 | News Media Ads | [5 empty] | 0 |  |  | 0
IV-3 | LODGING, MEALS, INCIDENTALS | 360 | 0 | 1440 | 1800 |  | 0 | 0 | 0% | 0 | 1800
IV-3.1 | Hotel Costs | [5 empty] | 0 |  |  | 0
IV-3.2 | Meal Costs | [5 empty] | 0 |  |  | 0
IV-3.3 | Incidentals | [5 empty] | 0 |  |  | 0
IV-4 | POSTAGE | 100 | 0 | 400 | 500 |  | 0 | 0 | 0% | 0 | 500
IV-4.1 | Mailings | [5 empty] | 0 |  |  | 0
IV-5 | REGISTRATION / TRAINING | 484 | 0 | 1936 | 2420 |  | 0 | 0 | 0% | 0 | 2420
IV-5.1 | Conference Registration | [5 empty] | 0 |  |  | 0
IV-5.2 | Meeting / Workshop / Training Fees | [5 empty] | 0 |  |  | 0
IV-6 | TRAVEL | 1100 | 0 | 4400 | 5500 |  | 0 | 0 | 0% | 0 | 5500
IV-6.1 | Mileage Reimbursement | [5 empty] | 0 |  |  | 0
IV-6.2 | Car Rental Costs | [5 empty] | 0 |  |  | 0
IV-6.3 | Other Travel Expenses | [5 empty] | 0 |  |  | 0
V. INDIRECT COSTS | [6 empty] | V. INDIRECT COSTS
IV-1 | INDIRECT COSTS | 6394.8 | 0 | 25579.2 | 31974 |  | 0 | 0 | 0% | 0 | 31974
IV-1.1 | Incurred Indirect Costs | [5 empty] | 0 |  |  | 0
TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total: | 0 | 0 | 0% | 0 | 132969
[6 empty] | Federal Share: | 0 | 0 |  | 0 | 106375.2
[6 empty] | Local Share: | 0 | 0 |  | 0 | 26593.8
[6 empty] | RPO Operations Q2 reimbursement |  | 0
RPO Operational Expense TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total Expense | 0 | 0 | 0% | 0 | 132969

## Q2 Narrative
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
2nd Quarter Narrative
Foothills RPO
I. DATA COLLECTION AND ASSESSMENT
I-1 DATA COLLECTION AND ASSESSMENT |  | 0
I-1.1 | Highway | 0
I-1.2 | Other Modes | 0
I-1.3 | Socioeconomic | 0
I-1.4 | Title VI | 0
II. TRANSPORTATION PLANNING
II-1 COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT |  | 0
II-1.1 | Develop CTP Vision | 0
II-1.2 | Conduct CTP Needs Assessment | 0
II-1.3 | Analyze Alternatives and Environmental Screening | 0
II-1.4 | Develop Final Plan | 0
II-1.5 | Adopt Plan | 0
II-2 PRIORITIZATION |  | 0
II-2.1 | Project Prioritization | 0
II-3 PROGRAM AND PROJECT DEVELOPMENT |  | 0
II-3.1 | STIP Participation | 0
II-3.2 | Merger / Project Development | 0
II-4 GENERAL TRANSPORTATION PLANNING |  | 0
II-4.1 | Regional and Statewide Planning | 0
II-4.2 | Special Studies, Projects and Other Trainings | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 ADMINISTRATIVE ACTIVITIES |  | 0
III-1.1 | Administrative Documents | 0
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance | 0
III-1.3 | Program Administration | 0
IV. DIRECT COSTS
IV-1 PROGRAMMATIC DIRECT CHARGES |  | 0
IV-1.1 | Program-wide Direct Costs | 0
IV-2 ADVERTISING |  | 0
IV-2.1 | News Media Ads | 0
IV-3 LODGING, MEALS, INCIDENTALS |  | 0
IV-3.1 | Hotel Costs | 0
IV-3.2 | Meal Costs | 0
IV-3.3 | Incidentals | 0
IV-4 POSTAGE |  | 0
IV-4.1 | Mailings | 0
IV-5 REGISTRATION / TRAINING |  | 0
IV-5.1 | Conference Registration | 0
IV-5.2 | Meeting / Workshop / Training Fees | 0
IV-6 TRAVEL |  | 0
IV-6.1 | Mileage Reimbursement | 0
IV-6.2 | Car Rental Costs | 0
IV-6.3 | Other Travel Expenses | 0
V. INDIRECT COSTS
V-1 INDIRECT COSTS APPROVED BY COGNIZANT AGENCY |  | 0
V-1.1 | Incurred Indirect Costs | 0
RPO Operational Expense TOTAL |  | 0

## Q3 Expenditures
FY 2023 (July 1, 2022-June 30, 2023) | [5 empty] | FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM | [5 empty] | 3rd QUARTER - QUARTERLY EXPENDITURE SUMMARY
ANNUAL FUNDING SOURCES TABLE | [5 empty] | Foothills RPO
Foothills RPO
TASK CODE | WORK CATEGORY | RPO PROGRAM FUNDS |  |  |  |  | RPO Expenditures - 3rd Quarter expenses incurred January 1 - March 31
|  | LOCAL 20% | STATE 0% | Federal 80% | TOTAL |  | 1st QUARTER EXPENDITURES | 2nd QUARTER EXPENDITURES | 3rd QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
I. DATA COLLECTION AND ASSESSMENT | [6 empty] | I. DATA COLLECTION AND ASSESSMENT
I-1 | DATA COLLECTION AND ASSESSMENT | 2000 | 0 | 8000 | 10000 |  | 0 | 0 | 0 | 0% | 0 | 10000
I-1.1 | Highway | [5 empty] | 0 | 0 |  |  | 0
I-1.2 | Other Modes | [5 empty] | 0 | 0 |  |  | 0
I-1.3 | Socioeconomic | [5 empty] | 0 | 0 |  |  | 0
I-1.4 | Title VI | [5 empty] | 0 | 0 |  |  | 0
II. TRANSPORTATION PLANNING | [6 empty] | II. TRANSPORTATION PLANNING
II-1 | CTP DEVELOPMENT | 1300 | 0 | 5200 | 6500 |  | 0 | 0 | 0 | 0% | 0 | 6500
II-1.1 | Develop CTP Vision | [5 empty] | 0 | 0 |  |  | 0
II-1.2 | Conduct CTP Needs Assessment | [5 empty] | 0 | 0 |  |  | 0
II-1.3 | Analyze Alternatives and Environmental Screening | [5 empty] | 0 | 0 |  |  | 0
II-1.4 | Develop Final Plan | [5 empty] | 0 | 0 |  |  | 0
II-1.5 | Adopt Plan | [5 empty] | 0 | 0 |  |  | 0
II-2 | PRIORITIZATION | 1000 | 0 | 4000 | 5000 |  | 0 | 0 | 0 | 0% | 0 | 5000
II-2.1 | Project Prioritization | [5 empty] | 0 | 0 |  |  | 0
II-3 | PROGRAM AND PROJECT DEVELOPMENT | 2850 | 0 | 11400 | 14250 |  | 0 | 0 | 0 | 0% | 0 | 14250
II-3.1 | STIP Participation | [5 empty] | 0 | 0 |  |  | 0
II-3.2 | Merger / Project Development | [5 empty] | 0 | 0 |  |  | 0
II-4 | GENERAL TRANSPORTATION PLANNING | 4900 | 0 | 19600 | 24500 |  | 0 | 0 | 0 | 0% | 0 | 24500
II-4.1 | Regional and Statewide Planning | [5 empty] | 0 | 0 |  |  | 0
II-4.2 | Special Studies, Projects and Other Trainings | [5 empty] | 0 | 0 |  |  | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES | [6 empty] | III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 | ADMINISTRATIVE ACTIVITIES | 3700 | 0 | 14800 | 18500 |  | 0 | 0 | 0 | 0% | 0 | 18500
III-1.1 | Administrative Documents | [5 empty] | 0 | 0 |  |  | 0
III-1.2 | TCC/TAC Work Facilitation; Ethics Compliance | [5 empty] | 0 | 0 |  |  | 0
III-1.3 | Program Administration | [5 empty] | 0 | 0 |  |  | 0
IV. DIRECT COSTS | [6 empty] | IV. DIRECT COSTS
IV-1 | PROGRAMMATIC DIRECT CHARGES | 2305 | 0 | 9220 | 11525 |  | 0 | 0 | 0 | 0% | 0 | 11525
IV-1.1 | Program-wide Direct Costs | [5 empty] | 0 | 0 |  |  | 0
IV-2 | ADVERTISING | 100 | 0 | 400 | 500 |  | 0 | 0 | 0 | 0% | 0 | 500
IV-2.1 | News Media Ads | [5 empty] | 0 | 0 |  |  | 0
IV-3 | LODGING, MEALS, INCIDENTALS | 360 | 0 | 1440 | 1800 |  | 0 | 0 | 0 | 0% | 0 | 1800
IV-3.1 | Hotel Costs | [5 empty] | 0 | 0 |  |  | 0
IV-3.2 | Meal Costs | [5 empty] | 0 | 0 |  |  | 0
IV-3.3 | Incidentals | [5 empty] | 0 | 0 |  |  | 0
IV-4 | POSTAGE | 100 | 0 | 400 | 500 |  | 0 | 0 | 0 | 0% | 0 | 500
IV-4.1 | Mailings | [5 empty] | 0 | 0 |  |  | 0
IV-5 | REGISTRATION / TRAINING | 484 | 0 | 1936 | 2420 |  | 0 | 0 | 0 | 0% | 0 | 2420
IV-5.1 | Conference Registration | [5 empty] | 0 | 0 |  |  | 0
IV-5.2 | Meeting / Workshop / Training Fees | [5 empty] | 0 | 0 |  |  | 0
IV-6 | TRAVEL | 1100 | 0 | 4400 | 5500 |  | 0 | 0 | 0 | 0% | 0 | 5500
IV-6.1 | Mileage Reimbursement | [5 empty] | 0 | 0 |  |  | 0
IV-6.2 | Car Rental Costs | [5 empty] | 0 | 0 |  |  | 0
IV-6.3 | Other Travel Expenses | [5 empty] | 0 | 0 |  |  | 0
V. INDIRECT COSTS | [6 empty] | V. INDIRECT COSTS
IV-1 | INDIRECT COSTS | 6394.8 | 0 | 25579.2 | 31974 |  | 0 | 0 | 0 | 0% | 0 | 31974
IV-1.1 | Incurred Indirect Costs | [5 empty] | 0 | 0 |  |  | 0
TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total: | 0 | 0 | 0 | 0% | 0 | 132969
[6 empty] | Federal Share: | 0 | 0 | 0 |  | 0 | 106375.2
[6 empty] | Local Share: | 0 | 0 | 0 |  | 0 | 26593.8
[6 empty] | RPO Operations Q3 reimbursement |  |  | 0
RPO Operational Expense TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total Expense | 0 | 0 | 0 | 0% | 0 | 132969

## Q3 Narrative
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
3rd Quarter Narrative
Foothills RPO
I. DATA COLLECTION AND ASSESSMENT
I-1 DATA COLLECTION AND ASSESSMENT |  | 0
I-1.1 | Highway | 0
I-1.2 | Other Modes | 0
I-1.3 | Socioeconomic | 0
I-1.4 | Title VI | 0
II. TRANSPORTATION PLANNING
II-1 COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT |  | 0
II-1.1 | Develop CTP Vision | 0
II-1.2 | Conduct CTP Needs Assessment | 0
II-1.3 | Analyze Alternatives and Environmental Screening | 0
II-1.4 | Develop Final Plan | 0
II-1.5 | Adopt Plan | 0
II-2 PRIORITIZATION |  | 0
II-2.1 | Project Prioritization | 0
II-3 PROGRAM AND PROJECT DEVELOPMENT |  | 0
II-3.1 | STIP Participation | 0
II-3.2 | Merger / Project Development | 0
II-4 GENERAL TRANSPORTATION PLANNING |  | 0
II-4.1 | Regional and Statewide Planning | 0
II-4.2 | Special Studies, Projects and Other Trainings | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 ADMINISTRATIVE ACTIVITIES |  | 0
III-1.1 | Administrative Documents | 0
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance | 0
III-1.3 | Program Administration | 0
IV. DIRECT COSTS
IV-1 PROGRAMMATIC DIRECT CHARGES |  | 0
IV-1.1 | Program-wide Direct Costs | 0
IV-2 ADVERTISING |  | 0
IV-2.1 | News Media Ads | 0
IV-3 LODGING, MEALS, INCIDENTALS |  | 0
IV-3.1 | Hotel Costs | 0
IV-3.2 | Meal Costs | 0
IV-3.3 | Incidentals | 0
IV-4 POSTAGE |  | 0
IV-4.1 | Mailings | 0
IV-5 REGISTRATION / TRAINING |  | 0
IV-5.1 | Conference Registration | 0
IV-5.2 | Meeting / Workshop / Training Fees | 0
IV-6 TRAVEL |  | 0
IV-6.1 | Mileage Reimbursement | 0
IV-6.2 | Car Rental Costs | 0
IV-6.3 | Other Travel Expenses | 0
V. INDIRECT COSTS
V-1 INDIRECT COSTS APPROVED BY COGNIZANT AGENCY |  | 0
V-1.1 | Incurred Indirect Costs | 0
RPO Operational Expense TOTAL |  | 0

## Q4 Expenditures
FY 2023 (July 1, 2022-June 30, 2023) | [5 empty] | FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM | [5 empty] | 4th QUARTER - QUARTERLY EXPENDITURE SUMMARY
ANNUAL FUNDING SOURCES TABLE | [5 empty] | Foothills RPO
Foothills RPO
TASK CODE | WORK CATEGORY | RPO PROGRAM FUNDS |  |  |  |  | RPO Expenditures --4th Quarter expenses incurred April 1 - June 30
|  | LOCAL 20% | STATE 0% | Federal 80% | TOTAL |  | 1st QUARTER EXPENDITURES | 2nd QUARTER EXPENDITURES | 3rd QUARTER EXPENDITURES | 4th QUARTER EXPENDITURES | % BUDGET SPENT TO DATE | TO DATE EXPENDITURES | BUDGETED AMOUNT
I. DATA COLLECTION AND ASSESSMENT | [6 empty] | I. DATA COLLECTION AND ASSESSMENT
I-1 | DATA COLLECTION AND ASSESSMENT | 2000 | 0 | 8000 | 10000 |  | 0 | 0 | 0 | 0 | 0% | 0 | 10000
I-1.1 | Highway | [5 empty] | 0 | 0 | 0 |  |  | 0
I-1.2 | Other Modes | [5 empty] | 0 | 0 | 0 |  |  | 0
I-1.3 | Socioeconomic | [5 empty] | 0 | 0 | 0 |  |  | 0
I-1.4 | Title VI | [5 empty] | 0 | 0 | 0 |  |  | 0
II. TRANSPORTATION PLANNING | [6 empty] | II. TRANSPORTATION PLANNING
II-1 | CTP DEVELOPMENT | 1300 | 0 | 5200 | 6500 |  | 0 | 0 | 0 | 0 | 0% | 0 | 6500
II-1.1 | Develop CTP Vision | [5 empty] | 0 | 0 | 0 |  |  | 0
II-1.2 | Conduct CTP Needs Assessment | [5 empty] | 0 | 0 | 0 |  |  | 0
II-1.3 | Analyze Alternatives and Environmental Screening | [5 empty] | 0 | 0 | 0 |  |  | 0
II-1.4 | Develop Final Plan | [5 empty] | 0 | 0 | 0 |  |  | 0
II-1.5 | Adopt Plan | [5 empty] | 0 | 0 | 0 |  |  | 0
II-2 | PRIORITIZATION | 1000 | 0 | 4000 | 5000 |  | 0 | 0 | 0 | 0 | 0% | 0 | 5000
II-2.1 | Project Prioritization | [5 empty] | 0 | 0 | 0 |  |  | 0
II-3 | PROGRAM AND PROJECT DEVELOPMENT | 2850 | 0 | 11400 | 14250 |  | 0 | 0 | 0 | 0 | 0% | 0 | 14250
II-3.1 | STIP Participation | [5 empty] | 0 | 0 | 0 |  |  | 0
II-3.2 | Merger / Project Development | [5 empty] | 0 | 0 | 0 |  |  | 0
II-4 | GENERAL TRANSPORTATION PLANNING | 4900 | 0 | 19600 | 24500 |  | 0 | 0 | 0 | 0 | 0% | 0 | 24500
II-4.1 | Regional and Statewide Planning | [5 empty] | 0 | 0 | 0 |  |  | 0
II-4.2 | Special Studies, Projects and Other Trainings | [5 empty] | 0 | 0 | 0 |  |  | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES | [6 empty] | III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 | ADMINISTRATIVE ACTIVITIES | 3700 | 0 | 14800 | 18500 |  | 0 | 0 | 0 | 0 | 0% | 0 | 18500
III-1.1 | Administrative Documents | [5 empty] | 0 | 0 | 0 |  |  | 0
III-1.2 | TCC/TAC Work Facilitation; Ethics Compliance | [5 empty] | 0 | 0 | 0 |  |  | 0
III-1.3 | Program Administration | [5 empty] | 0 | 0 | 0 |  |  | 0
IV. DIRECT COSTS | [6 empty] | IV. DIRECT COSTS
IV-1 | PROGRAMMATIC DIRECT CHARGES | 2305 | 0 | 9220 | 11525 |  | 0 | 0 | 0 | 0 | 0% | 0 | 11525
IV-1.1 | Program-wide Direct Costs | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-2 | ADVERTISING | 100 | 0 | 400 | 500 |  | 0 | 0 | 0 | 0 | 0% | 0 | 500
IV-2.1 | News Media Ads | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-3 | LODGING, MEALS, INCIDENTALS | 360 | 0 | 1440 | 1800 |  | 0 | 0 | 0 | 0 | 0% | 0 | 1800
IV-3.1 | Hotel Costs | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-3.2 | Meal Costs | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-3.3 | Incidentals | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-4 | POSTAGE | 100 | 0 | 400 | 500 |  | 0 | 0 | 0 | 0 | 0% | 0 | 500
IV-4.1 | Mailings | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-5 | REGISTRATION / TRAINING | 484 | 0 | 1936 | 2420 |  | 0 | 0 | 0 | 0 | 0% | 0 | 2420
IV-5.1 | Conference Registration | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-5.2 | Meeting / Workshop / Training Fees | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-6 | TRAVEL | 1100 | 0 | 4400 | 5500 |  | 0 | 0 | 0 | 0 | 0% | 0 | 5500
IV-6.1 | Mileage Reimbursement | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-6.2 | Car Rental Costs | [5 empty] | 0 | 0 | 0 |  |  | 0
IV-6.3 | Other Travel Expenses | [5 empty] | 0 | 0 | 0 |  |  | 0
V. INDIRECT COSTS | [6 empty] | V. INDIRECT COSTS
IV-1 | INDIRECT COSTS | 6394.8 | 0 | 25579.2 | 31974 |  | 0 | 0 | 0 | 0 | 0% | 0 | 31974
IV-1.1 | Incurred Indirect Costs | [5 empty] | 0 | 0 | 0 |  |  | 0
TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total: | 0 | 0 | 0 | 0 | 0% | 0 | 132969
[6 empty] | Federal Share: | 0 | 0 | 0 | 0 |  | 0 | 106375.2
[6 empty] | Local Share: | 0 | 0 | 0 | 0 |  | 0 | 26593.8
[6 empty] | RPO Operations Q4 reimbursement |  |  |  | 0
RPO Operational Expense TOTAL |  | 26593.8 | 0 | 106375.2 | 132969 | Total Expense | 0 | 0 | 0 | 0 | 0 | 0 | 132969

## Q4 Narrative
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
4th Quarter Narrative
Foothills RPO
I. DATA COLLECTION AND ASSESSMENT
I-1 DATA COLLECTION AND ASSESSMENT |  | 0
I-1.1 | Highway | 0
I-1.2 | Other Modes | 0
I-1.3 | Socioeconomic | 0
I-1.4 | Title VI | 0
II. TRANSPORTATION PLANNING
II-1 COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT |  | 0
II-1.1 | Develop CTP Vision | 0
II-1.2 | Conduct CTP Needs Assessment | 0
II-1.3 | Analyze Alternatives and Environmental Screening | 0
II-1.4 | Develop Final Plan | 0
II-1.5 | Adopt Plan | 0
II-2 PRIORITIZATION |  | 0
II-2.1 | Project Prioritization | 0
II-3 PROGRAM AND PROJECT DEVELOPMENT |  | 0
II-3.1 | STIP Participation | 0
II-3.2 | Merger / Project Development | 0
II-4 GENERAL TRANSPORTATION PLANNING |  | 0
II-4.1 | Regional and Statewide Planning | 0
II-4.2 | Special Studies, Projects and Other Trainings | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 ADMINISTRATIVE ACTIVITIES |  | 0
III-1.1 | Administrative Documents | 0
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance | 0
III-1.3 | Program Administration | 0
IV. DIRECT COSTS
IV-1 PROGRAMMATIC DIRECT CHARGES |  | 0
IV-1.1 | Program-wide Direct Costs | 0
IV-2 ADVERTISING |  | 0
IV-2.1 | News Media Ads | 0
IV-3 LODGING, MEALS, INCIDENTALS |  | 0
IV-3.1 | Hotel Costs | 0
IV-3.2 | Meal Costs | 0
IV-3.3 | Incidentals | 0
IV-4 POSTAGE |  | 0
IV-4.1 | Mailings | 0
IV-5 REGISTRATION / TRAINING |  | 0
IV-5.1 | Conference Registration | 0
IV-5.2 | Meeting / Workshop / Training Fees | 0
IV-6 TRAVEL |  | 0
IV-6.1 | Mileage Reimbursement | 0
IV-6.2 | Car Rental Costs | 0
IV-6.3 | Other Travel Expenses | 0
V. INDIRECT COSTS
V-1 INDIRECT COSTS APPROVED BY COGNIZANT AGENCY |  | 0
V-1.1 | Incurred Indirect Costs | 0
RPO Operational Expense TOTAL |  | 0

## Yearly Narrative
FY 2023 (July 1, 2022-June 30, 2023)
PLANNING WORK PROGRAM
Yearly Narrative
Foothills RPO
I. DATA COLLECTION AND ASSESSMENT
I-1 DATA COLLECTION AND ASSESSMENT |  | 0
I-1.1 | Highway | 0
I-1.2 | Other Modes | 0
I-1.3 | Socioeconomic | 0
I-1.4 | Title VI | 0
II. TRANSPORTATION PLANNING
II-1 COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT |  | 0
II-1.1 | Develop CTP Vision | 0
II-1.2 | Conduct CTP Needs Assessment | 0
II-1.3 | Analyze Alternatives and Environmental Screening | 0
II-1.4 | Develop Final Plan | 0
II-1.5 | Adopt Plan | 0
II-2 PRIORITIZATION |  | 0
II-2.1 | Project Prioritization | 0
II-3 PROGRAM AND PROJECT DEVELOPMENT |  | 0
II-3.1 | STIP Participation | 0
II-3.2 | Merger / Project Development | 0
II-4 GENERAL TRANSPORTATION PLANNING |  | 0
II-4.1 | Regional and Statewide Planning | 0
II-4.2 | Special Studies, Projects and Other Trainings | 0
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
III-1 ADMINISTRATIVE ACTIVITIES |  | 0
III-1.1 | Administrative Documents | 0
III-1.2 | TCC / TAC Work Facilitation; Ethics Compliance | 0
III-1.3 | Program Administration | 0
IV. DIRECT COSTS
IV-1 PROGRAMMATIC DIRECT CHARGES |  | 0
IV-1.1 | Program-wide Direct Costs | 0
IV-2 ADVERTISING |  | 0
IV-2.1 | News Media Ads | 0
IV-3 LODGING, MEALS, INCIDENTALS |  | 0
IV-3.1 | Hotel Costs | 0
IV-3.2 | Meal Costs | 0
IV-3.3 | Incidentals | 0
IV-4 POSTAGE |  | 0
IV-4.1 | Mailings | 0
IV-5 REGISTRATION / TRAINING |  | 0
IV-5.1 | Conference Registration | 0
IV-5.2 | Meeting / Workshop / Training Fees | 0
IV-6 TRAVEL |  | 0
IV-6.1 | Mileage Reimbursement | 0
IV-6.2 | Car Rental Costs | 0
IV-6.3 | Other Travel Expenses | 0
V. INDIRECT COSTS
V-1 INDIRECT COSTS APPROVED BY COGNIZANT AGENCY |  | 0
V-1.1 | Incurred Indirect Costs | 0
RPO Program TOTAL |  | 0
VI-1 | SPECIAL SPR ALLOCATION (Project #1) | 0
VI-1.1 | #REF! | 0
SPR SPECIAL PROJECT #1 TOTAL |  | 0
VI-1 | SPECIAL SPR ALLOCATION (Project #2) | 0
VI-1.2 | #REF! | 0
SPECIAL SPR PROJECT #2 TOTAL |  | 0

## Reference
Examples of Activities in Categories
I. DATA COLLECTION AND ASSESSMENT
| I-1 | DATA COLLECTION AND ASSESSMENT
|  | I-1.1 | Highway
CTP Inventory and Assessment
Parking Inventories
Vehicle Occupancy Rates (VOR) Counts and Assessment
Traffic Volume Counts and Assessment
Crash Data and Assessment
|  | I-1.2 | Non-Highway
Bicycle and Pedestrian Inventory and Assessment
Traffic Volume Counts and Assessment
Public Transportation Service Data and Assessment
Multimodal Data Collection and Assessment
Freight Data Collection and Assessment
|  | I-1.3 | Socioeconomic
Socioeconomic Data Inventory
Environmental and Land use Data Inventory and Assessment
Demographic Data Collection and Assessment
|  | 1-1.4 | Title VI
RPO Affirmation of Title VI Compliance
Transportation Initiatives and ADA Compliance
Environmental Justice Assessment
Limited English Proficiency (LEP) Assessment
II. TRANSPORTATION PLANNING
| II-1 | COMPREHENSIVE TRANSPORTATION PLAN (CTP) DEVELOPMENT
|  | II-1.1 | Develop CTP Vision
CTP Study Setup
Local CTP Vision
|  | II-1.2 | Conduct CTP Needs Assessment
Data Collection and Assessment
Current and Future Year Data Endorsements
Deficiency Assessment
|  | II-1.3 | Analyze Alternatives and Environmental Screening
Alternatives Assessment
Local Alternative Consensus
|  | II-1.4 | Develop Final Plan
Develop CTP Maps
Local Endorsement
|  | II-1.5 | Adopt Plan
CTP Document
CTP and Local Land Use Revisions
Development of Local Implementation Strategies
| II-2 | PRIORITIZATION
Project Prioritization
| II-3 | PROGRAM AND PROJECT DEVELOPMENT
|  | II-3.1 | STIP Participation
|  | II-3.2 | Merger / Project Development
Purpose and Need Data
Public Involvement Strategies
Meeting Attendance
Review and Comment
Indirect and Cumulative Effects
| II-4 | GENERAL TRANSPORTATION PLANNING
|  | II-4.1 | Regional and Statewide Planning
|  | II-4.2 | Special Studies, Projects and Other Training
III. ADMINISTRATION OF TRANSPORTATION PLANNING AND POLICIES
| III-1 | ADMINISTRATIVE ACTIVITIES
|  | III-1.1 | Administrative Documents
Planning Work Program
5-Year Planning Calendar
Quarterly Invoice and Progress Reports
|  | III-1.2 | TCC/TAC Work Facilitation; Ethics Compliance
Preparing for and holding Meetings
Ethics Compliance Activities
Regulatory Documents
|  | III-1.3 | Program Expenses
IV. DIRECT COSTS
| IV-1 | PROGRAMMATIC DIRECT CHARGES
|  | IV-1.1 | Program-wide Direct Costs
Communications
cell phone
communications
telecom
telephone
telephone and internet
telephone, cell service
telephone/postage
broadband
Dues and Subscriptions
dues and subscriptions
dues/memberships
Equipment
capital equipment
equipment - capital outlay
equipment maintenace and repair
equipment maintenance
equipment rent
copier
computer costs
maintenance and repair
Insurance
insurance
insurance and bonding
Occupancy Cost
building rent
cost of space
occupancy
occupancy expense
rent
building maintenance
maintenance and repair
utilities
Professional Services
audit
professional services
Supplies
copier costs/paper
office supplies
supplies
special materials
printing
printing, dues
IT
IT
IT system administration
CPU services, licensing & fees
computer services
contracted (computer/phone)
|  | IV-1.2 | Advertising
advertising
news media legal ads
|  | IV-1.3 | Lodging, Meals, Incidentasl
lodging
lodging and meals
meals
hotels, meals, incidentals
parking expense
|  | IV-1.4 | Postage
postage
shipping
|  | IV-1.5 | Registration/Training
meeting expense
meeting expense and conference registration
meetings and registration
registration fees
registration/travel
employee and board training
training
|  | IV-1.6 | Travel
travel
travel - other
travel and training
training and travel
vehicles usage
mileage and auto allowance
mileage expense
V. INDIRECT COSTS
| V-1 | INDIRECT COSTS APPROVED BY COGNIZAT AGENT FY 18-19
|  | V-1.1 | Incurred Indirect Costs

## Drop Down Functions
5%
10%
20%